# PROJECT OUTPLAY

Current State Report

What is built, what is in flight, and what comes next

Version 1.0

April 2026

[Studio Name]

[Author / Contact]

# Purpose of this Document

This document is an honest, current snapshot of Project Outplay. It is not a marketing piece. It exists so that anyone reviewing the project (a potential studio collaborator, an investor, a contractor) can understand exactly what has been built, what remains, and where the risks live.

The companion documents to this one are:

- Game Design Document v3 - the design vision, broadly stable

- Technical Design Document v2 - the engineering architecture and decisions

- Sprint Roadmap v2 - the phased delivery plan

# Project Status: Sprint 1 (in progress)

The project is in the middle of Sprint 1, which establishes the first single-player combat loop. Sprint 0 (foundations) is complete. Sub-sprints 1.1 through the start of 1.3 are complete. Sub-sprint 1.4 (damage numbers and hit feedback) and 1.5 (game feel tuning pass) are upcoming.

## What is built and verified

- Unity 6 LTS project with URP 2D rendering

- Repository structure with Git, Git LFS, conventional .gitignore and .gitattributes

- CLAUDE.md project guidelines committed and used by Claude Code

- Folder structure under Assets/_Project/ matching documented conventions

- Unity Input System installed with PlayerControls action map

- Player capsule with WASD movement, mouse aim, dash on Space

- Movement is weighted (acceleration, deceleration, top speed independently tunable)

- Single physics writer architecture (PlayerMover only writes to Rigidbody2D)

- PlayerVisual generates capsule and facing wedge in code

- Health and PlayerMana resource components with events and OnChanged subscription

- Screen-space HUD with red HP bar and blue Mana bar

- ResourceBar prefab and IResourceProvider interface (refactored after first two bars)

- Mana regenerates over time, drains on cast

- Firebolt projectile cast on left click

- ProjectileConfig as ScriptableObject with speed, lifetime, damage

- ProjectilePool using UnityEngine.Pool.ObjectPool

- Wand component with mana cost, fire cooldown, owner tracking

- Caster filter prevents projectile from hitting its own player

- Generic Health component (replaces PlayerHealth) with IDamageable interface

## What is in flight (Sprint 1, current)

- Dummy target with Health, kill detection, respawn timer

- World-space ResourceBar floating above the dummy

- Hit detection from projectile to IDamageable target

## What is up next (still in Sprint 1)

- Damage numbers (pooled UI elements that pop on hit)

- Hit VFX (particle burst on impact)

- Hit pause (1-2 frame freeze on significant hits)

- Audio cues for hit, kill, low HP

- Game feel tuning pass on movement and casting values

# Code and Asset Inventory

## Scripts

| Path | Purpose |
| --- | --- |
| Scripts/Player/PlayerInput.cs | Wraps Input System, exposes typed events |
| Scripts/Player/PlayerMover.cs | Weighted movement, single physics writer |
| Scripts/Player/PlayerAimer.cs | Free rotation following mouse |
| Scripts/Player/PlayerDash.cs | Enum-based state machine for dash |
| Scripts/Player/PlayerVisual.cs | Procedural capsule + wedge sprite |
| Scripts/Player/PlayerControls.cs | Generated Input System wrapper |
| Scripts/Player/PlayerMana.cs | Mana resource with regen |
| Scripts/Player/Wand.cs | Casting controller (mana, cooldown, spawn) |
| Scripts/Combat/Health.cs | Generic damageable component |
| Scripts/Combat/Projectile.cs | Pooled projectile with lifetime |
| Scripts/Combat/ProjectilePool.cs | Pool using UnityEngine.Pool.ObjectPool |
| Scripts/Combat/ProjectileConfig.cs | ScriptableObject for projectile params |
| Scripts/Core/IResourceProvider.cs | Interface for HP/Mana/cooldown bars |
| Scripts/Core/IDamageable.cs | Interface for damage application |
| Scripts/UI/PlayerHUD.cs | Wires HP and Mana bars to player resources |
| Scripts/UI/ResourceBar.cs | Reusable bar that binds to any IResourceProvider |

## Prefabs

| Path | Purpose |
| --- | --- |
| Prefabs/Player/Player.prefab | Player root with all components |
| Prefabs/Combat/Projectile.prefab | Pooled projectile template |
| Prefabs/UI/ResourceBar.prefab | Reusable resource bar |
| Prefabs/Enemies/Dummy.prefab | Dummy target template |

## Settings

| Path | Purpose |
| --- | --- |
| Settings/Combat/Firebolt.asset | Firebolt projectile config (speed 14, lifetime 2, damage 10) |

## Scenes

| Path | Purpose |
| --- | --- |
| Scenes/Arena_Test.unity | Sole gameplay scene; tests prototype flow |

# Validated Behaviors

These are behaviors that have been verified through interactive play in the editor. They are not promises about future features; they are confirmed working today.

- Player capsule moves with weighted feel; stutter-stepping changes momentum

- Movement does not exceed top speed on diagonals (input is normalized)

- Mouse aim updates the visible facing indicator instantly

- Dash on Space repositions the player ~3 units; cooldown of 1.2s prevents spam

- HUD shows HP at 100/100 (red) and Mana at 100/100 (blue)

- Mana regenerates at 5/sec when below max

- Mana decreases by 5 per Firebolt cast

- Firebolts spawn from the wand tip in the facing direction

- Firebolts travel at speed 14 for 2 seconds before despawn

- Firebolts do not hit the player who fired them

- Firebolts pool correctly: spawning many in succession reuses pool entries

- Cooldown between shots prevents firing faster than 4 shots per second

# Outstanding Verifications

These are behaviors expected to work but not yet confirmed via play because the relevant feature is not yet built or tested:

- Dummy takes damage from projectile hits

- Dummy HP bar updates as damage applies

- Dummy dies and respawns after 3 seconds

- Damage numbers appear on hit (Sprint 1.4)

- Hit VFX plays on projectile impact (Sprint 1.4)

# Architecture Highlights

Several architectural decisions made early in the project pay back over time. These are worth understanding by anyone joining the project.

## Single physics writer

Only PlayerMover writes to the player's Rigidbody2D. PlayerDash and any future system communicate via SetVelocityOverride and ClearVelocityOverride. This avoided a category of subtle race conditions where multiple components fight over the same physics body.

## Event-driven UI with initial sync in Start

UI components subscribe to OnChanged events in OnEnable but do their initial sync in Start, after all Awake calls have run. This pattern was discovered the hard way when the HUD initially showed 0/100 instead of 100/100; the fix taught a lesson that now applies project-wide.

## ResourceBar abstraction

After building HP and Mana bars as separate UI structures, we extracted a ResourceBar component and prefab plus an IResourceProvider interface. The dummy's HP bar uses the same prefab. Every future bar (cooldowns, boss HP, status meters) reuses the same components without writing new UI code.

## Object pooling from day one

Projectiles use Unity's built-in UnityEngine.Pool.ObjectPool from their first commit. We never had Instantiate/Destroy in combat code that needed refactoring later. Adding more spawned objects (damage numbers, VFX) follows the same pattern.

## ScriptableObject configurations

Static gameplay data (projectile speed, damage, lifetime) lives in ScriptableObject assets, not in code. The Firebolt config is one asset; future spell types are new assets, not new code.

## Caster ownership in projectiles

Projectiles store their casterRoot GameObject. Trigger collision logic ignores the caster. This prevents self-hit issues and threads the source through to IDamageable for future kill credit logic.

# Working Style

Project Outplay is being developed by a solo developer with active AI assistance from Claude (Anthropic). Two tools are used in distinct roles:

## Claude Code

Command-line agent with full repository access. Writes scripts, edits files, runs git commands, authors prefab and scene YAML when low-risk, hands off manual recipes when high-risk. Reads CLAUDE.md at every session for persistent project context.

## Claude.ai chat

Design partner for architectural discussions, code review, debugging stuck moments, and pacing decisions. Reviews scripts pasted from Claude Code before they are committed when the code is foundational.

## Review discipline

- Every commit is reviewed by the human developer before push

- Foundational code (player controller, combat, networking) gets a second-pass review

- Architectural changes require explicit human approval

- Generated tests are reviewed for actual coverage, not just green CI

## CLAUDE.md as living document

The CLAUDE.md file at the project root captures the operationally important facts: design pillars, tech stack, code conventions, hard "do not" list, and working style. It evolves as decisions are made. The most recent additions cover UI authoring policy (when YAML authoring is used vs. when manual recipes are handed off).

# Risk Snapshot

| Risk | Severity | Status |
| --- | --- | --- |
| Combat does not feel good in solo testing | Critical | Mitigated by ongoing tuning passes |
| Multiplayer netcode does not support skillshots at scale | Critical | Not yet tested; FishNet selected |
| Server costs exceed house rake | High | Modeled in TDD; entry tier floor identified |
| Legal classification as gambling | High | Deferred until traction; counsel engagement planned |
| Cheating destroys trust in paid mode | High | Server authority designed in; stat anomaly detection planned |
| Solo developer scope exhaustion | Medium | Sprint plan scoped to single-developer pace; AI assistance multiplies output |
| AI tooling outage interrupts development | Low | Multiple AI tools available as fallback (OpenCode, Codex) |
| Unity WebGL build size kills web retention | Medium | Build size budget set; aggressive stripping planned |

# Honest Gap Analysis

This section names what is genuinely missing. It is included for the same reason this document exists: a real status report is more valuable than a polished pitch.

## What this project does not have yet

- Multiplayer (Sprint 2)

- More than one wand archetype

- Any utility spells

- Any rune system

- Any gear system

- Any account or persistence layer

- Matchmaking

- Telemetry

- Real art (programmer art only)

- Audio (no SFX or music)

- Any payment or wallet integration

- Any anti-cheat infrastructure

- Real playtest data beyond solo dogfooding

- Any external testers

## What this project does have

- A coherent, written design document with stable pillars

- A documented technical architecture with rationale for major decisions

- A scoped sprint plan with verifiable exit criteria

- A working single-player movement and combat prototype

- Discipline around code conventions, server authority, and event-driven UI

- An AI-augmented development workflow that maintains review quality

## What it would take to bring this to closed beta

- 4-6 months of full-time work by the current solo developer to reach closed alpha

- Or 2-3 months with a second developer focused on networking and backend

- Some art investment (placeholder will not retain players past first session)

- A small live-ops engineer presence by the time of beta launch

- Legal counsel engagement before paid mode infrastructure ships

End of Current State Report v1.0 - April 2026 - Project Outplay